## Linen Management System
GANTT CHART | [8 empty] | Smartsheet Tip ➜ | [6 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  |  |  | Linen Management System |  |  |  |  | COMPANY NAME | [7 empty] | IG-MDT
PROJECT MANAGER | [8 empty] | DATE | [7 empty] | 2019-12-21
NO | TASK TITLE |  |  | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | 2019-12-01 | [23 empty] | 2020-01-01 | [23 empty] | 2020-02-01
[9 empty] | WEEK 1 | [5 empty] | WEEK 2 | [5 empty] | WEEK 3 | [5 empty] | WEEK 4 | [5 empty] | WEEK 1 | [5 empty] | WEEK 2 | [5 empty] | WEEK 3 | [5 empty] | WEEK 2 | [5 empty] | WEEK 1 | [5 empty] | WEEK 2 | [5 empty] | WEEK 3 | [5 empty] | WEEK 4
[9 empty] | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S | M | T | W | R | F | S
1 | User Requirement and Scop
1.1 | User Requirement Collection |  |  | MDT |  |  | 0 | 100%
1.2 | Flow Chart |  |  | MDT |  |  | 0 | 100%
1.3 | Sequence Diagram |  |  | IG | 2019-12-21 | 2019-12-25 | 4 | 40% | bar: WEEK 3 F to WEEK 4 M
1.4 | System Architecture |  |  | IG | 2019-12-21 | 2019-12-21 | 0 | 100% | bar: WEEK 3 S
2 | Mockup Design |  |  |  | 2019-12-21 | 2019-12-25 | 4
2.1 | Hotel |  |  | IG | 2019-12-21 | 2019-12-25 | 4 | 0% | bar: WEEK 3 S to WEEK 4 W
2.1.1 |  | Mobile Reader |  |  | 2019-12-21 | 2019-12-25 | 4 | 0% | bar: WEEK 3 S to WEEK 4 W
2.1.2 |  | Mobile App |  |  | 2019-12-21 | 2019-12-25 | 4 | 0% | bar: WEEK 3 S to WEEK 4 W
2.2 | Laundry Plant |  |  | IG | 2019-12-21 | 2019-12-25 | 4 | 0% | bar: WEEK 3 S to WEEK 4 W
2.2.1 |  | Mobile Reader |  |  | 2019-12-21 | 2019-12-25 | 4 | 0% | bar: WEEK 3 S to WEEK 4 W
2.2.2 |  | Mobile App |  |  | 2019-12-21 | 2019-12-25 | 4 | 0% | bar: WEEK 3 S to WEEK 4 W
2.2.3 |  | Back-office |  |  | 2019-12-21 | 2019-12-25 | 4 | 0% | bar: WEEK 3 S to WEEK 4 W
3 | System Development
3.1 | Hotel |  |  | IG |  |  | 0 | 0%
3.1.1 |  | Mobile Reader |  |  |  |  | 0 | 0%
3.1.1.1 |  |  | Login |  |  |  | 0 | 0%
3.1.1.2 |  |  | Logout |  |  |  | 0 | 0%
3.1.1.3 |  |  | Change Password |  |  |  | 0 | 0%
3.1.1.4 |  |  | Scan Soil |  |  |  | 0 | 0%
3.1.1.5 |  |  | Scan Stain |  |  |  | 0 | 0%
3.1.1.6 |  |  | Scan Torn |  |  |  | 0 | 0%
3.1.1.7 |  |  | Scan Clean |  |  |  | 0 | 0%
3.1.2 |  | Mobile App |  |  |  |  | 0 | 0%
3.1.2.1 |  |  | Login |  |  |  | 0 | 0%
3.1.2.2 |  |  | Logout |  |  |  | 0 | 0%
3.1.2.3 |  |  | Profile |  |  |  | 0 | 0%
3.1.2.4 |  |  | Change Password |  |  |  | 0 | 0%
3.1.2.5 |  |  | Received Push Notification |  |  |  | 0 | 0%
3.1.2.6 |  |  | Realtime Data |  |  |  | 0 | 0%
3.2 | Laundry Plant |  |  | IG |  |  | 0 | 0%
3.2.1 |  | Mobile Reader |  |  |  |  | 0 | 0%
3.2.1.1 |  |  | Login |  |  |  | 0 | 0%
3.2.1.2 |  |  | Logout |  |  |  | 0 | 0%
3.2.1.3 |  |  | Change Password |  |  |  | 0 | 0%
3.2.1.4 |  |  | Register Linen |  |  |  | 0 | 0%
3.2.1.5 |  |  | Scan Total |  |  |  | 0 | 0%
3.2.1.6 |  |  | Scan Stain |  |  |  | 0 | 0%
3.2.1.7 |  |  | Scan Torn |  |  |  | 0 | 0%
3.2.1.8 |  |  | Scan Clean |  |  |  | 0 | 0%
3.2.1.9 |  |  | Scan Discard |  |  |  | 0 | 0%
3.2.1.10 |  |  | Re-tag |  |  |  | 0 | 0%
3.2.2 |  | Mobile App |  |  |  |  | 0 | 0%
3.2.2.1 |  |  | Login |  |  |  | 0 | 0%
3.2.2.2 |  |  | Logout |  |  |  | 0 | 0%
3.2.2.3 |  |  | Profile |  |  |  | 0 | 0%
3.2.2.4 |  |  | Change Password |  |  |  | 0 | 0%
3.2.2.5 |  |  | Received Push Notification |  |  |  | 0 | 0%
3.2.2.6 |  |  | Realtime Data |  |  |  | 0 | 0%
3.2.2.7 |  |  | Inventory Summary |  |  |  | 0 | 0%
3.2.3 |  | Back-office |  |  |  |  | 0 | 0%
3.2.3.1 |  |  | Login |  |  |  | 0 | 0%
3.2.3.2 |  |  | Logout |  |  |  | 0 | 0%
3.2.3.3 |  |  | Change Password |  |  |  | 0 | 0%
3.2.3.4 |  |  | Reset Password |  |  |  | 0 | 0%
3.2.3.5 |  |  | Dashboard |  |  |  | 0 | 0%
3.2.3.6 |  |  | Hotel |  |  |  | 0 | 0%
3.2.3.7 |  |  | Linen Template |  |  |  | 0 | 0%
3.2.3.8 |  |  | Realtime Data |  |  |  | 0 | 0%
3.2.3.9 |  |  | User Management |  |  |  | 0 | 0%
3.2.3.10 |  |  | Linen Info |  |  |  | 0 | 0%
3.2.3.11 |  |  | Bill |  |  |  | 0 | 0%
3.2.3.12 |  |  | Report |  |  |  | 0 | 0%